7. PROJECT DEMONSTRATION PHASE

Automating Employee Data Import & Relationship Mapping Using Import Sets and Dot Walking

# DEMONSTRATION OBJECTIVES

The Demonstration Phase is the formal presentation of the completed ServiceNow automation solution to the project's key stakeholders. Its primary purpose is to provide stakeholders with direct, evidence-based confirmation that the solution functions as specified, before the project is formally closed and the solution is handed over to the operations team. This document governs the planning, execution, and recording of all demonstration and User Acceptance Testing activities.

This phase represents the transition point between development and operations. The solution has been built and internally verified during the Development Phase; the Demonstration Phase now invites the business and technical stakeholders who funded and scoped the project to observe the working system, validate it against the original requirements, and provide their formal acceptance. Until that acceptance is received, the project remains open and the development team retains responsibility for the solution.

## Success Criteria for This Phase

    - Requirements Validation: Stakeholders confirm, via live demonstration, that all six functional requirements (FR-01 through FR-05) and all applicable acceptance criteria (AC-01 through AC- 06) from the Requirement Analysis document are satisfied by the implemented solution.

    - UAT Completion: All critical and high-priority User Acceptance Test cases (TC-01 through TC- 07) have been executed, results recorded, and no outstanding Critical or High severity defects remain unresolved.

    - Formal Sign-Off: The Project Acceptance Form in Section 8 of this document has been signed by the Project Sponsor, Business Owner, IT Operations Manager, Service Desk Manager, and Project Manager.

    - Handover Readiness: The operations team confirms they have received and reviewed the Project Documentation Phase document (Phase 6) and are prepared to assume operational responsibility for the solution.

# DEMONSTRATION SCOPE

  - In-Scope for Demonstration

| Feature | What Will Be Shown | Requirement Ref. | Acceptance Criteria Ref. |
| --- | --- | --- | --- |
| Data Source Preparation | The prepared employee data CSV file with all five column headers and sample records, including manager references. | FR-01 | AC-01 |
| Import Set Upload | Navigation to Load Data, selection of [u_import_employee] table, file upload, and confirmation of records in the staging table. | FR-01, FR-02 | AC-01 |
| Transform Map Configuration | The configured Transform Map showing source table, target table, all five Field Maps including the coalesce setting on email and the manager mapping. | FR-03 | AC-02 |
| Transform Map Execution | Live execution of the Transform Map and confirmation of Completed status in the Transform History record. | FR-03 | AC-02 |
| User Record Verification | Navigation to [sys_user] to confirm four or more new user records with all fields populated, including the manager reference link. | FR-03 | AC-02, AC-03 |
| Incident Form Layout | The Incident form showing the three dot-walked fields: Assigned to Department, Assigned to Email, and Assigned to Manager. | FR-05 | AC-04, AC-05 |
| Auto-Population in Action | Live selection of an imported user in the Assigned to field and immediate auto-population of all three contextual fields. | FR-05 | AC-04, AC-05, AC-06 |
| Multi-User Update | Changing the Assigned to field to a different imported user and confirming the three fields refresh with the new user's data. | FR-05 | AC-06 |

# DEMONSTRATION LOGISTICS

## Attendees and Roles

The following roles are required to attend the demonstration session. Attendance by the Project Sponsor, Business Owner, and QA/UAT Lead is mandatory for formal sign-off. All other attendees should be confirmed at least five business days before the session. Blank name fields are to be completed by the Project Manager before the invitation is issued.

## Environment and Prerequisites

All prerequisites listed below must be confirmed as complete and verified by the ServiceNow Administrator at least 24 hours before the scheduled demonstration session. Any unresolved prerequisite must be escalated to the Project Manager immediately, as it may require the session to be rescheduled.

## Session Agenda

The following agenda governs the timing of the demonstration session. The Project Manager is responsible for keeping the session within the allotted time. Questions should be captured during the Q&A segment — interruptions during the demonstration steps should be noted and addressed after each feature block is complete.

| Time | Segment |
| --- | --- |
| 0:00 – 0:05 | Section 4.1 ¦ Introduction — Welcome, objectives review, scope confirmation, feedback process explanation |
| 0:05 – 0:15 | Section 4.2 ¦ Feature Demo: Data Import — Source file, Import Set navigation, file upload, staging table verification |
| 0:15 – 0:30 | Section 4.3 ¦ Feature Demo: Data Transformation — Transform Map review, live execution, Transform History, [sys_user] verification |
| 0:30 – 0:45 | Section 4.4 ¦ Feature Demo: Dot-Walking on Incident Form — Form layout, auto- population demo, multi-user refresh |
| 0:45 – 0:55 | Section 4.5 ¦ Q&A and Feedback — Open floor, feedback form completion, change request capture |
| 0:55 – 1:00 | Section 4.6 ¦ Closing — Outcomes summary, UAT timeline, sign-off process, next steps |

# DEMONSTRATION SCRIPT

4.1 Introduction

5 Minutes

Welcome attendees and introduce the presenter, facilitator, and any other team members present. Briefly state the objectives for the session: to show the working solution, confirm it meets the agreed requirements, and obtain formal acceptance. Confirm that all in-scope features will be covered and that out-of-scope items should be noted for future phases, not discussed today. Explain that a feedback form will be completed by each stakeholder after the demonstration, and that Q&A time is allocated at minute 45.

| 4.2 Feature Demonstration: Data Import | 10 Minutes |
| --- | --- |

| 4.3 Feature Demonstration: Data Transformation | 15 Minutes |
| --- | --- |

| 4.4 Feature Demonstration: Dot-Walking on Incident Form | 15 Minutes |
| --- | --- |

| 4.5 Q&A and Stakeholder Feedback | 10 Minutes |
| --- | --- |

4.6 Closing

5 Minutes

Summarise the features demonstrated and the acceptance criteria that were observed to be met during the session. Confirm the UAT timeline and the process for completing and returning the Stakeholder Feedback Form. Explain the sign-off process: once UAT is complete and no Critical or High severity defects remain open, the Project Acceptance Form in Section 8 will be circulated for signature. Thank all attendees for their time and participation.

# USER ACCEPTANCE TESTING (UAT) PLAN

## UAT Objectives

User Acceptance Testing is the formal structured testing phase conducted by designated business and technical representatives to validate that the solution meets all agreed requirements under realistic usage conditions. UAT is distinct from the internal testing performed during development — it is conducted by people who represent the intended users of the solution, not the team that built it.

## UAT Test Cases

The following eight test cases cover all in-scope features of the solution. Test cases TC-01 through TC-07 are classified as Critical — they must all pass before UAT sign-off can be obtained. TC-08 is classified as a Conditional Negative Test — it validates graceful failure behaviour when a manager reference cannot be resolved, and does not need to block sign-off if the behaviour is consistent with the design specification.

## UAT Schedule

The following schedule governs the UAT execution period. All dates are to be filled in by the Project Manager based on the confirmed demonstration session date. UAT should begin within two business days of the demonstration session to maintain project momentum.

## UAT Success Criteria

    - All eight test cases (TC-01 through TC-08) have been executed and results recorded in the UAT test case table.

    - All Critical and High severity test cases (TC-01 through TC-07) return a PASS status.

    - TC-08 returns either PASS or a documented KNOWN ISSUE with the agreed graceful failure behaviour confirmed.

    - No open defects with a severity rating of Critical or High remain unresolved in the defect log.

    - The Business Owner has confirmed verbally and in the UAT sign-off record that the solution meets the business requirements as defined in the Requirement Analysis document.

    - The Stakeholder Feedback Forms from Section 7 have been completed and returned by all mandatory attendees, with no 'Needs Improvement' or 'Poor' ratings on core functional criteria without a written explanation.

# DEFECT TRACKING AND RESOLUTION

## Defect Severity Levels

The following severity definitions govern the classification of all defects raised during the demonstration session and UAT execution. All defects must be classified using these definitions at the time of logging. Classification may be revised during triage if new information is available.

| Severity | Description | Resolution Requirement |
| --- | --- | --- |
| Critical | System cannot be demonstrated or core functionality is completely broken — Import Set upload fails, Transform Map does not execute, or dot-walked fields do not appear on the form. | Must be resolved before the demonstration can proceed or before UAT sign-off can be obtained. |
| High | A required feature does not function correctly and no workaround is available — for example, manager field remains unresolved for all records, or auto-population does not trigger. | Must be resolved before UAT sign-off. |
| Medium | A feature produces incorrect results in some scenarios but a workaround exists — for example, phone field unpopulated on some records but correctable by re- import. | Should be resolved before operational handover or formally documented as a known issue. |
| Low | Cosmetic or minor usability issues — for example, field label formatting, column ordering in staging table view. | May be deferred to a future enhancement cycle. |

## Defect Log

All defects identified during the demonstration session or UAT execution must be recorded in the following log by the QA / UAT Lead. Each entry must include a unique Defect ID (format: DEF-XXX), a clear description of the observed behaviour, reproducible steps, the assigned severity level, current status, the developer or administrator assigned to resolution, and the final resolution description once resolved.

Status values: Open (logged, not yet investigated), In Progress (under investigation or being fixed), Resolved (fix applied, awaiting retest), Closed (retested and confirmed fixed), Deferred (agreed to defer to future phase, documented as known issue).

# STAKEHOLDER FEEDBACK FORM

This feedback form is to be completed by each stakeholder attendee following the demonstration session. It may be completed during the Q&A segment or returned to the Project Manager within 24 hours of the session. The feedback collected here will inform the UAT process and any future enhancements.

Please rate each aspect of the solution using the scale provided (5 = Excellent, 1 = Poor). Use the Comments column for specific observations. Written feedback in the open-text fields below is particularly valuable for aspects that received a rating of 3 or below.

# PROJECT SIGN-OFF DOCUMENT

This section constitutes the formal Project Acceptance Form for the Employee Data Import and Relationship Mapping Automation project. By signing this form, each approver confirms that they have observed the demonstration of the completed solution, reviewed the UAT results, and are satisfied that the solution meets the requirements defined in the Requirement Analysis document.

This form may only be signed after all UAT success criteria defined in Section 5.4 have been confirmed as met by the QA / UAT Lead. A signed copy of this form should be retained in the project repository alongside the full project documentation series (Phases 1–7).

# DEMONSTRATION PHASE CHECKLIST

The following checklist tracks the completion of all administrative and operational tasks required to plan, execute, and formally close the Demonstration Phase. The Project Manager is responsible for maintaining this checklist. Each task should be marked complete only after it has been verified — not when it has been initiated. All items must be checked before the Demonstration Phase can be formally closed.

# CONCLUSION AND TRANSITION TO OPERATIONS

Upon successful completion of all activities in this Demonstration Phase document — including executed UAT, resolved defects, completed feedback forms, and a signed Project Acceptance Form — the project will formally transition from the delivery team to the operations and support team. This transition marks the end of the active project lifecycle and the beginning of the ongoing maintenance period governed by the Project Documentation Phase (Phase 6) document.

## Handover Items

The following items will be formally transferred to the IT Operations team upon project sign -off. The Project Manager is responsible for confirming receipt of each item with the IT Operations Manager before the project is archived.

| Handover Item | Description | Format | Status |
| --- | --- | --- | --- |
| Project Documentation Package (Phase 6) | Complete maintenance reference including admin guide, user guides, troubleshooting, and technical specifications. | Word Document | Delivered |
| Full Project Phase Document Series (Phases 1–7) | Complete project record: Identification, Requirements, Planning, Development, Design, Documentation, Demonstration. | Word Documents | Delivered |
| UAT Results Record | Completed test case table with actual results, tester names, and pass/fail status for all eight test cases. | This document (Section 5.2) | To be completed |
| Defect Log | Final defect log with all raised defects, severity classifications, resolution status, and any agreed deferrals. | This document (Section 6.2) | To be completed |
| Known Issues List | Any Medium or Low severity defects formally deferred to a future phase, with agreed workarounds documented. | Supplementary log if applicable | To be completed |
| Stakeholder Feedback Forms | Completed feedback forms from all mandatory demonstration attendees. | This document (Section 7) | To be completed |

## Post-Transition Responsibilities

    - Operational maintenance and monitoring: IT Operations team — refer to the routine maintenance schedule in Section 6.1 of the Project Documentation Phase document.

    - Incident and defect management: Any issues arising in production should be logged and triaged using the organisation's standard IT service management process and the troubleshooting guidance in Section 6.2 of the Project Documentation Phase document.

    - Future enhancements: Enhancement requests identified during UAT or post-go-live should be evaluated against the Enhancement Opportunities register in Section 6.3 of the Project Documentation Phase document and scoped as a new project if approved.

    - User training: The Project Documentation Phase document (Section 5) contains the role-specific user guides for Data Administrators and Service Desk Agents. These should be made available to all users via the organisation's standard training or knowledge base platform.