3. PROJECT PLANNING PHASE

Automating Employee Data Import & Relationship Mapping Using Import Sets and Dot Walking

# EXECUTIVE SUMMARY

This document constitutes the formal Project Planning Phase output for the ServiceNow Automation Project. Building upon the scope boundary established in the Identification Phase and the detailed requirements defined in the Requirement Analysis, this plan provides the structured framework within which the project will be executed, monitored, and closed.

The project objective is to configure the ServiceNow platform to automate the ingestion of new employee records from an externally prepared data file and to enable the Incident form to display contextually relevant user-related information — specifically, the assigned user's department, email address, and reporting manager — without requiring manual data retrieval by service desk personnel. The solution leverages ServiceNow's native Import Sets, Transform Maps, and dot-walking capabilities, and does not require custom scripting or external system integration.

The project is expected to be delivered in a single, linear phase by a ServiceNow administrator working within a development or Personal Developer Instance (PDI) environment. The total estimated effort is eight working days, encompassing data preparation, platform configuration, transformation execution, Incident form customisation, and end-to-end validation. The plan below summarises the key parameters at a glance.

The key deliverables of this project are: a configured Import Set staging table for employee data; a validated Transform Map with complete field mappings including the manager reference relationship; confirmed user records in the [sys_user] table following transformation; and a customised Incident form displaying dot-walked fields. All deliverables must satisfy the acceptance criteria reaffirmed in Section 8 of this document before the project is considered complete.

# PROJECT SCOPE CONFIRMATION

## In-Scope Items

    - Creation of an Import Set staging table (e.g., 'import employee') to receive and temporarily hold employee data records uploaded via a CSV or Excel source file.

    - Configuration of a Transform Map to define the source-to-target field mapping relationship between the Import Set staging table and the core User table [sys_user], including all five fields specified in the Data Dictionary.

    - Field mapping encompassing both direct (auto-mapped) matches for Name, Email, Department, and Phone Number, and the manual relationship mapping required for the Manager reference field.

    - Execution of the Transform Map to migrate staged records into the [sys_user] table and verification that the resulting user records are correctly populated, including resolved manager reference linkages.

    - Configuration of the Incident form layout to include three dot-walked fields — Assigned to Department, Assigned to Email, and Assigned to Manager — derived from the User record referenced in the 'Assigned to' field.

    - End-to-end testing and validation to confirm that all acceptance criteria defined in Section 8 are met prior to project closure.

## Out-of-Scope Items

    - Automated or scheduled data import processes. The solution addresses a manually triggered, file-based upload mechanism only; no recurring automation is planned in this phase.

    - Error handling routines, exception notification workflows, or data validation logic beyond the standard field mapping behaviour provided natively by the ServiceNow Transform Map engine.

    - Integration with live external HR or workforce management systems via API, middleware, MID Server, or any real-time data feed. The sole data input mechanism is a static CSV or Excel file prepared outside the platform.

    - Security configuration, role-based access control, or Access Control List (ACL) management related to the Import Set module, staging table, or modified Incident form.

    - Modification to any ServiceNow tables, forms, or processes beyond those explicitly defined: the Import Set staging table, the User table [sys_user], and the Incident form [incident].

# PROJECT TIMELINE & MILESTONES

| ID | Milestone | Description | Duration | Dependency |
| --- | --- | --- | --- | --- |
| M1 | Data Source Preparation | Prepare and validate the employee data source file. Create the source dataset containing the required fields (Name, Email, Department, Manager, Phone Number) for a representative sample set of employee records. Export or save the file in CSV or Excel format ready for upload. | 1 Day | None |
| M2 | Import Set Configuration | Upload the prepared source file into ServiceNow via the Import Sets module. Confirm that the platform creates the Import Set record and auto-generates the staging table (e.g., 'import employee') with all source columns correctly reflected. Inspect the staging table to verify that records are present and data is intact. | 1 Day | M1 |
| M3 | Transform Map Development | Create the Transform Map configuration linking the 'import employee' staging table to the [sys_user] target table. Execute the auto-mapping function to establish direct field matches. Manually configure the mapping for the Manager reference field to establish the correct relational linkage. Save and review all mappings prior to execution. | 2 Days | M2 |
| M4 | Data Transformation Execution | Execute the Transform Map against the staged Import Set records. Confirm that the transformation completes with a status of 'Completed'. Navigate to the [sys_user] table and inspect the resulting records | 1 Day | M3 |
| M5 | Incident Form Configuration | Access the Incident form layout configuration interface and add the three dot-walked fields to the form: Assigned to Department, Assigned to Email, and Assigned to Manager. Save and publish the updated form layout. Create a test Incident record to confirm that the fields are visible and positioned correctly on the form. | 1 Day | M4 |

- RESOURCE ALLOCATION

The following table identifies the roles, responsibilities, and estimated effort for each resource contributing to the project. Given the contained scope of this engagement, the project is designed to be deliverable by a small, focused team. The ServiceNow Administrator carries the primary configuration burden; all other roles provide input, oversight, or validation support at defined points in the timeline.

| Role | Responsibilities | Estimated Effort | Key Activities |
| --- | --- | --- | --- |
| Project Sponsor | IT Director or Service Management Owner. Provides executive mandate, approves the project plan, and makes decisions on scope or resource escalations. | 2–4 hours total | Plan approval; milestone sign-off; project closure confirmation. |
| Project Manager | Responsible for maintaining the project timeline, coordinating stakeholder communication, tracking milestones, and escalating risks. | 8–10 hours over 8 days | Kickoff facilitation; weekly status reporting; risk log maintenance; closure walkthrough. |
| ServiceNow Administrator / Developer | Primary technical resource. Responsible for all hands-on configuration: Import Sets, Transform Map, field mappings, and Incident form layout. | 40 hours over 8 days (full- time equivalent) | All M1–M6 milestone activities; technical documentation updates; defect remediation during validation. |
| Data Owner / HR Representative | Provides and validates the source employee data file. Confirms that imported user records are accurate and that manager relationships reflect the correct organisational reporting structure. | 3–5 hours total | Data file creation (M1); post- transformation record validation (M4); sign-off on data accuracy. |
| QA / Tester | Conducts structured testing of the end-to-end solution during M6. Verifies Incident form field population and documents results against acceptance criteria. | 8–12 hours during M6 | Test case execution (M6); acceptance criteria verification; defect logging. |

# TECHNICAL DEPENDENCIES & PREREQUISITES

## Platform Access

    - An active ServiceNow Personal Developer Instance (PDI) or dedicated development environment must be available and accessible to the ServiceNow Administrator prior to the commencement of M2.

    - The administrator must hold sufficient platform privileges to create and modify Import Set tables, configure Transform Mapsthe 'import_admin' and 'admin' roles are required for the relevant modules.

    - The development environment must be running a compatible and fully functional release of the ServiceNow platform. No additional plugins or instance configurations beyond standard out-of- the-box functionality are required for this project.

## Source Data File

    - The employee data source file must be prepared and validated by the Data Owner before M2 commences. correspond to the expected field names: Name, Email, Department, Manager, and Phone Number.

    - The source file must contain a minimum of four employee records to satisfy the acceptance criteria defined in Section 8. Records should be representative of actual organisational data, including at least one manager-employee relationship pair.

    - The Project Manager must confirm receipt of the validated source file from the Data Owner and store it in the agreed project documentation repository before the M2 start date.

## Manager Record Prerequisite

    - Manager records must exist in the [sys_user] table at the time the Transform Map is executed against employee records. If manager records are not yet present, the manager reference field will fail to resolve, resulting in incomplete employee records.

    - Where both manager and employee records are included in the same import batch, the import and transformation sequence must be designed to process manager records before any dependent employee records. This sequencing must be planned and confirmed during M3.

    - The text value used to identify managers in the source data file (e.g., a manager's full name or username) must exactly match the corresponding identifier field used for reference resolution in the Transform Map configuration, as agreed during M3.

# RISK ASSESSMENT & MITIGATION STRATEGIES

| Risk Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Data Format Mismatch Column headers in the source CSV or Excel file do not align with the expected field names, causing the auto- mapping function to fail or produce incorrect mappings. | Medium | Medium | The Data Owner must review and validate the source file structure against the field specification in the Data Dictionary (Requirement Analysis, Section 6) before uploading. A file template with pre-defined headers should be provided to the Data Owner at the project kickoff to eliminate ambiguity. |
| Manager Reference Resolution Failure The Manager field in the source data does not match any existing user record in [sys_user], resulting in the manager relationship not being established during transformation. | Medium | High | Before executing the full transformation, a pilot run using a single record should be performed to verify that the manager reference resolves correctly. The administrator must confirm that all referenced manager records are present in [sys_user] prior to the full execution. Processing sequence for manager-before-employee must be planned and tested during M3. |
| Dot-Walking Fields Failing to Populate Dot-walked fields added to the Incident form do not auto-populate when a user is selected, due to incorrect field path configuration or missing values in the related user record. | Low | Medium | Validate dot-walking configuration using a single user record before completing the full form layout. Confirm that the field traversal path is correctly specified (e.g., assigned_to.department) and that the related user record has values populated in the required fields. Testing with the imported sample records should be performed during M6 before sign-off. |
| Scope Creep Stakeholders introduce requests for additional fields, automation logic, or extended functionality during the implementation phase that fall outside the agreed project scope. | Medium | Low | The in-scope and out-of-scope items defined in this document (Section 2) must be reviewed and signed off at the project kickoff meeting. Any requests for changes during implementation must be formally logged as change requests and assessed against the project timeline and budget before acceptance. The Project Manager is responsible for enforcing this boundary. |

- COMMUNICATION PLAN

The following communication plan defines the structured interactions that will take place across the project lifecycle to ensure that all stakeholders remain informed, risks are surfaced promptly, and milestone completions are formally acknowledged. Adherence to this plan is the responsibility of the Project Manager.

| Communication Event | Frequency | Audience | Purpose & Content |
| --- | --- | --- | --- |
| Project Kickoff Meeting | Once — prior to M1 | All stakeholders | Review and confirm project objectives, scope, roles, and timeline. Distribute this planning document for sign-off. Confirm access to the ServiceNow instance and agree on the source data file delivery date with the Data Owner. |
| Weekly Status Update | Weekly — throughout project | Project Manager, Sponsor, ServiceNow Administrator | Concise written summary of milestones completed, current progress against plan, active risks, and planned activities for the following week. Distributed by email; no formal meeting required unless a risk escalation is in progress. |
| Milestone Review Checkpoint | At completion of M2, M3, M4, and M5 | Project Manager, ServiceNow Administrator, Data Owner (M2 & M4), Sponsor (M3 & M5) | Structured walkthrough of the completed milestone deliverable. Confirm that the milestone acceptance criteria are met before marking it as complete and authorising commencement of the next milestone. Document the outcome in the project log. |
| Testing & Validation Review | Once — during M6 | All stakeholders | QA tester presents the results of the end-to- end test execution against all acceptance criteria. Service Desk Manager observes and confirms Incident form behaviour. Any failed criteria are logged as defects for remediation before final sign-off. |
| Project Closure & Handover | Once — upon M6 completion | All stakeholders | Final walkthrough of the delivered solution. Handover of all project documentation (Identification Phase, Requirement Analysis, and Planning Phase documents) to the ServiceNow Administrator as the ongoing operational owner. Formal sign-off by the Project Sponsor. |

# NEXT STEPS

The following immediate actions are required to formally initiate the project following approval of this planning document. Each action is assigned a responsible party and a brief note on the expected outcome. These steps must be completed before Milestone 1 activities can commence.

| 1 | Project Manager | Distribute this planning document for stakeholder review and formal sign-off | Signed approval from the Project Sponsor is required before any project activity is initiated. Distribute within 24 hours of document completion. |
| --- | --- | --- | --- |

| 2 | Project Manager | Schedule and conduct the project kickoff meeting with all stakeholders | Review scope, timeline, roles, and communication plan. Confirm all parties understand their responsibilities and the project start date. |
| --- | --- | --- | --- |

| 3 | ServiceNow Administrator | Confirm access to the ServiceNow PDI or development environment | Verify administrative privileges are in place for Import Sets, Transform Maps, and Incident form configuration. Raise an access request immediately if privileges are insufficient. |
| --- | --- | --- | --- |

| 4 | Data Owner / HR Representative | Prepare and deliver the source employee data file in CSV or Excel format | File must conform to the column structure defined in the Data Dictionary. Delivery to the Project Manager is required before the M2 start date. A file template will be provided at the kickoff meeting. |
| --- | --- | --- | --- |

| 5 | Project Manager | Confirm manager records exist (or are included) in the source data file | Verify the prerequisite defined in Section 5.3. If manager records are absent from [sys_user], coordinate with the Data Owner to include them in the same import batch or arrange a prior import. |
| --- | --- | --- | --- |

| 6 | ServiceNow Administrator | Commence Milestone 1 — Data Source Preparation | Begin once the data file template has been confirmed and the kickoff meeting has been held. Target completion within one working day to maintain the planned eight-day timeline. |
| --- | --- | --- | --- |